## Defect Report
ClimaWatch Bug Tracking
Defect ID | Date | Module/Page Name | Description | Status | Enviroment | AssignedTo | Raised By | Issue Type | Severity | Priority
1 | 2022-08-02 | M-2 | Registration failed but backend showing all users information | CLOSED | Python | Bipul Chaudhary | Bipul Chaudhary and Shaquera Moore | Funtional | Critical | High
2 | 2022-08-03 | Homepage | News cards started to not work properly | CLOSED | Javascript | Kareem Bute | Kareem Bute and Bipul Chaudhary | Funtional | Moderate | Medium
3 | 2022-08-04 | M-4 | When user added current location to favorites then another user tried to add the same location it wasn't added | CLOSED | Python | Bipul Chaudhary | Bipul Chaudhary | Funtional | Critical | High
4 | 2022-08-08 | M-4 | Created location from the database wasn't able to be deleted | CLOSED | Dbreaver | Bipul Chaudhary | Bipul Chaudhary and Shaquera Moore | Funtional | Critical | Medium
5 | 2022-08-08 | M-1 | Clock display was showing AM when current time was PM | CLOSED | Javascript | Bipul Chaudhary | Bipul Chaudhary | Content | Cosmetic | Low
6 | 2022-08-11 | M-2 | When username is left blank for the registration form a new user is created instead of throwing an error | CLOSED | Dbreaver | Bipul Chaudhary | Shaquera Moore | Funtional | Critical | High
7 | 2022-08-12 | M-4/Homepage | When current location is clicked the weather for current location does not load | CLOSED | Javascript | Bipul Chaudhary | Kareem Bute, Bipul Chaudhary and Shaquera Moore | Funtional | Moderate | Medium